## INSTRUCTIONS - READ THIS FIRST
Please read the following before you start using the SARE tool:
· A diagram outlining the SARE stages is on the top right of this page.
· The worksheet, Summary (S0-S5), shows the activities that need to be completed in each category for each stage. This worksheet can be used as a reference point to show progression for each category as you move from one stage to the next.
· There are 7 categories of activities – each category has its own worksheet. These worksheets will not be visible until you have read the instructions and confirmed at the end of this sheet.
· There are a number of questions or statements for each category, which relate to different activities that need to be completed in order to move to the next stage.
· The first column tells you which stage each activity belongs to. Please ensure that you check this column before answering the question, as this will help to put the activity into its proper context.
· Each question/statement needs a response in the ‘Status’ column – you need to enter "0" under Status if No or None, or "1" if Yes. You must change 0 to 1 if you have a positive answer. If you don’t know the answer, enter “0” and put a comment in the associated ‘Remarks’ column. Once you know the answer, please update the spreadsheet.
· Where thought necessary, other important information has been provided next to each activity.
· Please note: Where there is no question related to the scale of an activity (particularly in the case of activities related to Stage 0 and Stage 1), the presence of that item is sufficient to obtain a 'yes' score, whether at country or local level. For example, “is there (human) rabies vaccine available in the country” - this may be just in one location, or everywhere in the country - both will give a 'yes' answer.
· Your scores will automatically be calculated on the ‘Summary (Score)’ worksheet, which will also tell you the remaining activities you need to complete for each stage, and display your current stage.
· You will be able to see your resulting SARE stage on the ‘Summary (Score)’ worksheet.
· You will be able to see details of all activities pending and completed for each stage on the ‘Summary (S0-S5)’ worksheet.
The Stepwise Approach towards Rabies Elimination:
A planning and evaluation tool
SARE may serve as a self-assessment and a practical guide in developing a national rabies program and to successfully implement the different described stages. It helps to achieve the goals set out in the Global Framework for the Elimination of Dog-Mediated Human Rabies. This tool is not prescriptive and it is not intended to replace existing regional or national rabies control strategies.
The SARE tool, when used in conjunction with the Canine Rabies Blueprint, provides practical guidance and examples of how to implement rabies control activities, as well as guidance on institutional responsibilities concerning each activity and who might carry out the work.
This tool will be most effective when used along with the SARE manual, which explains the steps and outlines key activities needed to progress along the stages.
The SARE tool provides measurable steps, designed as a logical flow of activities, to progress from Stage 0 (S0), being endemic for rabies, to Stage 5 (S5), which is freedom from dog-transmitted rabies.
The Stepwise Approach towards Rabies Elimination (SARE) has been developed as a template that countries may use to develop activities and measure progress towards a national programme and strategy for sustainable rabies prevention, control and eventually elimination.
This tool focuses on the prevention of dog-transmitted human rabies.
Click here for more information on STOP-R
I have read and understood the instructions above.

## Country profile
| Country: |  | Liberia |  | (You may select your country's name from the drop-down list)
| Prepared by: |  |  | Roseline George
HUMAN HEALTH: |  | Designation: |  | Deputy Director
|  | Office: |  | Division of Infectious Disease and Epidemiology
|  | Date prepared: |  | 2017-09-13 |  | (The date may appear as month-date-year or date-month-year depending on your computer's settings)
| Prepared by: |  |  | Leelia R. Andrews
ANIMAL HEALTH: |  | Designation: |  | Veterinary Epidemiologist
|  | Office: |  | Ministry of Agriculture
|  | Date prepared: |  | 2017-09-13 |  | (The date may appear as month-date-year or date-month-year depending on your computer's settings)
Prepared by:
OTHERS: |  | Designation:
Office:
|  | Date prepared: |  |  |  | (The date may appear as month-date-year or date-month-year depending on your computer's settings)
NAMES OF MEMBERS OF NATIONAL RABIES TASK FORCE: |  | There is not a National Rabies Task Force established yet, but there exists a National Rabies Technical Working Group.
The Rabies TWG consists of members from key line ministries and stakeholders and partners including:
Ministry of Agriculture
Ministry of Health
Forestry Development Authority
City Corperations
Environmenta Protection Agency
Ministry of Justice
National Public Health Institute
Partners (WHO, CDC, Predict, P&R, FAO)

## country (hidden)
Afghanistan
Africa
Aland Islands
Albania
Algeria
American Samoa
Andorra
Angola
Anguilla
Antarctica
Antigua & Barbuda
Argentina
Armenia
Aruba
Asia
Australia
Austria
Azerbaijan
Bahamas, The
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bermuda
Bhutan
Bolivia
Bonaire, St.Eustat, Saba
Bosnia and Herzegovina
Botswana
Bouvet Island
Brazil
British Indian Ocean T.
British Virgin Islands
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Caribbean, the
Cayman Islands
Central African Republic
Central America
Chad
Chile
China
Christmas Island
Cocos (Keeling) Islands
Colombia
Comoros
Congo
Congo, Dem. Rep. of the
Cook Islands
Costa Rica
Cote D'Ivoire
Croatia
Cuba
Curaçao
Cyprus
Czech Republic
Denmark
Djibouti
Dominica
Dominican Republic
East Timor (Timor-Leste)
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Europe
European Union
Falkland Is. (Malvinas)
Faroe Islands
Fiji
Finland
France
French Guiana
French Polynesia
French Southern Terr.
Gabon
Gambia, the
Georgia
Germany
Ghana
Gibraltar
Greece
Greenland
Grenada
Guadeloupe
Guam
Guatemala
Guernsey and Alderney
Guiana, French
Guinea
Guinea-Bissau
Guinea, Equatorial
Guyana
Haiti
Heard & McDonald Is.
Holy See (Vatican)
Honduras
Hong Kong, (China)
Hungary
Iceland
India
Indonesia
Iran, Islamic Republic of
Iraq
Ireland
Israel
Italy
Ivory Coast (Cote d'Ivoire)
Jamaica
Japan
Jersey
Jordan
Kazakhstan
Kenya
Kiribati
Korea Dem. People's Rep.
Korea, (South) Republic of
Kosovo
Kuwait
Kyrgyzstan
Lao People's Dem. Rep.
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Macao, (China)
Macedonia, TFYR
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Man, Isle of
Marshall Islands
Martinique (FR)
Mauritania
Mauritius
Mayotte (FR)
Mexico
Micronesia, Fed. States of
Middle East
Moldova, Republic of
Monaco
Mongolia
Montenegro
Montserrat
Morocco
Mozambique
Myanmar (ex-Burma)
Namibia
Nauru
Nepal
Netherlands
Netherlands Antilles
New Caledonia
New Zealand
Nicaragua
Niger
Nigeria
Niue
Norfolk Island
North America
Northern Mariana Islands
Norway
Oceania
Oman
Pakistan
Palau
Palestinian Territory
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Pitcairn Island
Poland
Portugal
Puerto Rico
Qatar
Reunion (FR)
Romania
Russia (Russian Fed.)
Rwanda
Sahara, Western
Saint Barthelemy (FR)
Saint Helena (UK)
Saint Kitts and Nevis
Saint Lucia
Saint Martin (FR)
S Pierre & Miquelon(FR)
S Vincent & Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South America
S.George & S.Sandwich
South Sudan
Spain
Sri Lanka (ex-Ceilan)
Sudan
Suriname
Svalbard & Jan Mayen Is.
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Taiwan
Tajikistan
Tanzania, United Rep. of
Thailand
Timor-Leste (East Timor)
Togo
Tokelau
Tonga
Trinidad & Tobago
Tunisia
Turkey
Turkmenistan
Turks and Caicos Is.
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom
United States
US Minor Outlying Isl.
Uruguay
Uzbekistan
Vanuatu
Vatican (Holy See)
Venezuela
Viet Nam
Virgin Islands, British
Virgin Islands, U.S.
Wallis and Futuna
Western Sahara
Yemen
Zambia
Zimbabwe

## Data coll & ax
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
1 | Surveillance | Are dog rabies cases reported from a local to the national level? |  | 0 | There is no structure in place for reporting dog rabies cases in the animal health sector | 3.1.3-Infrastructure-surveillance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | Zoonotic diseases : a guide to establishing collaboration | 6. Reporting of rabies data
1 |  | Are human rabies cases reported from a local to the national level? |  | 1 | There's an existing reporting structure of human rabies cases from local to national levels using the IDSR guidelines | 3.1.3-Infrastructure-surveillance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | Zoonotic diseases : a guide to establishing collaboration | 6. Reporting of rabies data
1 |  | Are all human or animal rabies testing results being reported to a relevant international database such as WHO, OIE or PARACON? |  | 0 |  | 6.7 International databases
1 |  | Is there capacity to analyze dog rabies data at the national level? | For example, data analysis infrastructure in place for other diseases/programmes, adequately trained staff, sufficient technology, etc. | 0 |  | 3.1.3-Infrastructure-surveillance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | 2.3 Animal rabies surveillance
1 |  | Is there capacity to analyze human rabies data at the national level? | For example, data analysis infrastructure in place for other diseases/programmes, adequately trained staff, sufficient technology, etc. | 1 |  | 3.1.3-Infrastructure-surveillance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | 2.2 Human rabies surveillance
1 |  | Has an animal rabies surveillance* system been established at the national level? |  | 0 | The process to establish a surveillance system is ongoing with full support from FAO | 3.1.3-Infrastructure-surveillance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | Zoonotic diseases : a guide to establishing collaboration | 2.3 Animal rabies surveillance
1 |  | Has a human rabies surveillance* system been established at the national level? |  | 1 | There is functional surveillance system established at all levels with surveillance focal persons | 3.1.3-Infrastructure-surveillance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | Zoonotic diseases : a guide to establishing collaboration | 2.2 Human rabies surveillance
1 |  | Have reports on the number of humans bitten by dogs been compiled and reviewed? |  | 1 | its compliled, reviewed and placed in the weekly Epi bullettin | 5.3.1-Rabies-surveillance
1 |  | Have dog population studies and KAP surveys been conducted to determine size, turn-over and accessibility of dogs for vaccination on a small scale? | Mention the years in which the studies were conducted | 0 |  | 5.4.1-estimate the number of dogs
2 |  | Have linked human and animal rabies surveillance systems, including agreed SOPs, been established? | Please describe the surveillance systems briefly, showing how data are shared. Note: Implementation of these linked measures is covered under 'Prevention and Control' | 0
2 |  | Are human rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? | Timeliness (e.g. monthly or real time) of reporting and feedback, feedback mechanisms established and stakeholders involved with clear reporting channels. (Follows on from establishment of data analysis capacity above) | 1 |  | 5.1.1-epidemiology-of-rabies | WHO International Health Regulations
2 |  | Are animal rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? | Timeliness (e.g. monthly or real time) of reporting and feedback, feedback mechanisms established and stakeholders involved with clear reporting channels. (Follows on from establishment of data analysis capacity above) | 0 | establishment of system in progress | 5.1.1-epidemiology-of-rabies | OIE Terrestrial Animal Health Code
2 |  | Is information on the epidemiology of rabies regularly shared with all stakeholders? | Stakeholders involved - for example, policy makers, educators, NGOs and other relevant individuals and organisations | 1 | Information on dog bite cases are shared with stakeholders using the human health Epi Bullettin | 5.1.1-epidemiology-of-rabies | WHO International Health Regulations | OIE Terrestrial Animal Health Code | 2. Roles-and-Responsibilities
2 |  | Is the on-going surveillance system for rabies being maintained? |  | 1 | For human health | WHO International Health Regulations | OIE Terrestrial Animal Health Code
3 |  | Have field investigations for all suspected human rabies cases been conducted? | Data shared between human and animal sectors in real time and joint actions taken | 0 | Not for all cases | 2.2 Human rabies surveillance
3 |  | Is epidemiological evidence available to rule out dog-transmitted human rabies cases? |  | 0
3 |  | Has an advocacy plan been approved by the government for local level implementation? |  | 0
3 |  | Are field investigations and laboratory confirmations conducted for all suspected rabies outbreaks in dogs? |  | 0
4 |  | Are existing surveillance activities for all suspected cases in humans maintained in the country? | Please answer '1' only if you have adequate functional surveillance based on your answers for earlier stages. | 0
4 |  | Has the epidemiological data from the routine surveillance of all animals (working animals, livestock and wildlife) been used to refine the national rabies strategy? |  | 0 |  | WHO International Health Regulations
3 | Health economic studies | Has the collection of local or national health economic and/or other disease prioritization tool data* on rabies control been initiated to make the case for rabies control investment? |  | 0 |  | Public-health-and-economic-burden-of rabies | Health economic studies on rabies
3 |  | Have the health economic data and/or other disease prioritization tool analyses been expanded to support further prioritization within the national rabies control programme? |  | 0 |  | Health economic studies on rabies | Comparing-PEP-costs
*Definitions
| Surveillance | Surveillance means the systematic ongoing collection, collation, and analysis of information related to human and animal health and the timely dissemination of information to those who need to know so that action can be taken. (Adapted from the OIE Terrestrial Animal Health Code 2010). It is the flow of data up to the national level and back down to the local level where activities are implemented.
| Health economics | Health economics is the discipline of economics applied to the topic of health care. It helps with the analysis of decision-making by individuals, health care providers and governments with respect to health and health care.
T
S
P
O
-R
echnical
DATA COLLECTION AND ANALYSIS

## Prev & Ctrl
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
1 | Human vaccines | Are vaccines for human rabies prophylaxis available in one or more parts of the country? |  | 1 | Available in all parts of the country | 5.5.3-human-biologics | Human-vaccination-supply
1 |  | Has the supply and access to WHO pre-qualified human rabies vaccines for PrEP for professionals at risk been ensured in local areas? |  | 0
2 |  | Has an assessment* been done to determine the availability and access to PEP (and PreP)? |  | 0 |  | 3.1-Infrastructure
2 |  | Are WHO pre-qualified human rabies vaccines available and accessible in most parts of the country? | Areas available and accessible | 1 |  | WHO expert consultation on rabies | WHO vaccines position papers
2 |  | Are any human biologics that are not WHO-pre-qualified being phased out? (e.g. nerve tissue vaccines, low quality vaccines) | If only WHO pre-qualified humans rabies vaccines are being used, mark the status as "1" | 1 |  | WHO prequalified vaccines list
3 |  | Is WHO pre-qualified Pre- and Post- Exposure Prophylaxis available and accessible to high risk and exposed individuals throughout the country? |  | 1 |  | WHO prequalified vaccines list
5 |  | Have modified protocols for PEP administration for rabies-free areas been implemented? |  | 0 |  | WHO expert consultation on rabies |  | Guidelines on human prophylaxis
1 | Dog vaccines | Are dog rabies vaccines available in at least one location in the country? |  | 0 |  | 3.1-Infrastructure
1 |  | Has dog vaccination been initiated in some parts of the country? | Areas covered | 0 |  | 5.4-What-are-we-going-to-do-dog-component
2 |  | Are only quality dog vaccines in accordance with OIE standards being used? |  | 0 |  | OIE terrestrial-manual
2 |  | Are dog vaccination campaigns regularly implemented in response to human cases and animal outbreaks? |  | 0 |  | 5.4-What-are-we-going-to-do-dog-component
3 |  | Are mass dog vaccination campaigns reaching at least 70% of the total dog population conducted according to the national rabies strategy? |  | 0 |  | 5.4.13-Vaccination campaign-coverage
3 |  | Are post-vaccination surveys* in dogs being carried out to evaluate vaccination coverage? | Briefly describe post-vaccination survey | 0 |  | 5.6-Evaluation
4 |  | Are dog vaccination campaigns maintained in zones where dog rabies is still present or where otherwise justified (e.g. risk of introduction)? |  | 0
5 |  | Based on risk assessments, are dog vaccination campaigns being maintained where justified? |  | 0 |  | 5.4-What-are-we-going-to-do-dog-component
1 | Outbreak response and other rabies control activities | Has Integrated Bite Case Management (IBCM)* been implemented at a local level? |  | 0 |  | Operational-activities
1 |  | Have Standard Operating Procedures (SOPs) for coordinated action on reported outbreaks* been established? |  | 0 |  | Challenges of animal health information systems and surveillance for animal diseases and zoonoses
2 |  | Have IBCM SOPs, including sharing of information between sectors, been agreed upon? | Sectors involved. | 0 |  | WHO expert consultation on rabies | Challenges of animal health information systems and surveillance for animal diseases and zoonoses | Zoonotic diseases: A guide to collaboration
2 |  | Are SOPs available for the observation of dogs involved in biting incidents? |  | 0 |  | Guidelines-animal-shelters | WHO expert consultation on rabies
2 |  | Have facilities or protocols been established for the observation of rabies-suspected dogs? | Home quarantine is adequate so long as the owner ensures the dog is provided sufficient food, water and shelter during the observation period. | 0 |  | Guidelines-animal-shelters
3 |  | Is there capacity to conduct field investigations and planned outbreak responses for animal and human rabies cases in the entire country? | Agencies of personnel involved in field investigations and outbreak response | 1 | limited capacities | WHO International Health Regulations | Challenges of animal health information systems and surveillance for animal diseases and zoonoses
3 |  | Have potential rabies-free zones been identified where canine variant cases have been absent for at least a 2 year period? | Names of rabies-free zones | 0 |  | 5.4.17 Keeping an area rabies-free
3 |  | Has dialogue been initiated with neighbouring countries to prevent the re-introduction of rabies into designated rabies-free zones? |  | 0 |  | 5.4.17-successful-maintenance | Challenges of animal health information systems and surveillance for animal diseases and zoonoses
4 |  | Has freedom from dog-transmitted rabies in the entire country been verified by the absence of canine variant cases for at least a 2 year period? |  | 0 |  | 5.4.17 Keeping an area rabies-free
4 |  | Has an emergency response/contingency plan been developed to address any reintroduced case of animal rabies involving a canine variant? |  | 0 |  | 5.4.20 Reintroduction response
5 |  | Has the capacity for outbreak and re-introduction response been maintained? |  | 0 |  | 5.4.17-successful-maintenance
* Definitions
| Assessment on access to PEP and PrEP | Determination of the extent to which people can actually obtain post-exposure and pre-exposure treatment. This may differ from the availability of the vaccine, because other factors such as the cost and location of the vaccine influence access.
| Post-vaccination surveys in dogs | Any survey conducted after a mass vaccination campaign has been implemented, and is used to determine the percentage of the dog population that has been vaccinated.
| IBCM | Integrated Bite Case Management (IBCM) is a coordinated One Health approach to managing human dog bite cases, with the goal of improved communication and data sharing between the animal health and human health sectors following a bite case. It has a positive impact on animal rabies surveillance, identification of additional human exposures (bite cases), reduction in human rabies cases, and helps to target emergency canine vaccinations to areas where there are confirmed canine rabies cases.
| Coordinated action on reported outbreaks | When an outbreak is reported, the human and animal health services need to work in collaboration to ensure that it is investigated and dealt with effectively. SOPs should be created so that everyone understands their roles in an outbreak.
T
S
P
O
-R
echnical
PREVENTION AND CONTROL

## Lab dx
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
0 | Specimen referral | Have contacts with an international rabies reference laboratory or international collaborating/reference center been established? | Names of international rabies reference laboratories or collaborating/reference centers | 1 | FAO Reference Lab, PADOVA, Rome, Italy | 3.1.7 Which laboratories are-available | OIE reference laboratories | WHO collaborating centres | FAO reference centre | WHO expert consultation on rabies
0 |  | Has at least one human or animal rabies suspect sample been submitted to an international rabies reference laboratory for confirmation? | Year of most recent specimen referral; Name of international rabies reference laboratory | 1 | 2017 to FAO reference Lab | Simple-techniques-for animal brain-sampling | 3.6 Human samples
1 | Laboratory capacity and testing | Is there capacity to conduct rabies diagnosis in at least one national laboratory (veterinary or medical laboratory)? |  | 1 | Central Veterinary Laboratory has the capacity to conduct rabies diagnosis, but needs strengthening | 3.1.8 Minimum laboratory requirements | OIE Manual of Diagnostic Tests and Vaccines for Terrestrial Animals | Laboratory biorisk management/
1 |  | Have several rabies suspect samples of animals or humans been submitted to a national laboratory and analysed? | Name of national laboratory; Laboratory test used | 1 | Central Veterinary Laboratory | Simple-techniques-for animal brain-sampling | Manual of Diagnostic Tests and Vaccines for Terrestrial Animals 2016 | WHO guidance on regulations for the transport of infectious substances
1 |  | Is animal rabies diagnosis conducted in at least one national laboratory? |  | 1 |  | 4. Laboratory rabies diagnosis
1 |  | Are rabies suspect samples of animals or humans submitted twice yearly to an international laboratory and analysed? |  | 0 |  | 6.7 International databases
2 |  | Is there regular laboratory diagnosis of animal rabies cases in country? | Name and location of laboratories; how often (regularly) samples are diagnosed | 0 | not regular | 3.1.8 Minimum laboratory requirements | Laboratory biorisk management
2 |  | Has capacity for regular sample collection and transportation been established and functioning? | Capacity includes the following: costing and payment system for sample transport, contact persons, transport companies/vehicles, packaging etc. | 0 |  | OIE Manual of Diagnostic Tests and Vaccines for Terrestrial Animals | Laboratory biorisk management | 5.3.1-Rabies-surveillance
3 |  | Are wildlife samples submitted for rabies laboratory diagnosis? |  | 0
3 |  | Is access to reliable laboratory diagnosis available throughout the country for animal samples (and if possible also for human and wildlife samples)? | Names and locations of laboratories | 0 |  | 3.1.8-laboratory diagnosis | 4. Laboratory rabies diagnosis
3 |  | Is there regular characterization and analysis of circulating rabies virus variants by a national or international laboratory? | Name of laboratory/institute where molecular tests are being performed | 0 |  | OIE reference laboratories | WHO collaborating centres | WHO expert consultation on rabies | FAO reference centre
4 |  | Is there maintenance of existing surveillance activities, including ongoing laboratory investigation, for all suspected cases in dogs in the country? |  | 0 |  | OIE Terrestrial Animal Health Code
5 |  | Are there on-going laboratory investigations of all suspected cases in domestic and wild animal species in the country? |  | 0 |  | OIE Terrestrial Animal Health Code
LABORATORY DIAGNOSIS
T
S
P
O
-R
echnical

## Dog popn
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
1 |  | Have discussions been held with stakeholders to create a dog population management strategy at a local level? | Stakeholders involved, how this integrates with rabies control strategy. Studies and surveys from "Prevention and Control" need to be completed before this item. | 1 | discussions have been held among stakeholders | 5.4.16 Dog population management tools | Guidelines-dog-population-management
1 |  | Have you involved officials in waste management in your stakeholder meetings | Removal of garbage or preventing animals from reaching the garbage takes away available food sources for dogs. This will help to reduce the number of free-roaming dogs in the community. | 1 | Environmental Protenction Agency, City Corporations
2 |  | Has a DPM* strategy and programmebeen drafted and shared with all relevant stakeholders at a local level? |  | 0
2 |  | Has the DPM strategy been finalized? |  | 0
2 |  | Has public sensitisation about DPM been built into rabies awareness campaigns at a local level? |  | 0
2 |  | Has dog population management been implemented at a local level? | Please list what strategies are currently being used. NOTE: Mass culling is NOT considered an effective DPM strategy. However, controlled euthanasia of suspect rabid animals is considered appropriate. | 0 |  | Monitoring and evaluation of dog population management programmes
2 |  | Have training or refresher courses on animal handling and sterilisation been initiated for professionals in animal health at a local level? |  | 0 |  | GARC Animal Handling and Vaccination course
3 |  | Has the DPM strategy been assessed and refined based on current dog ecology or KAP surveys? |  | 0 |  | Knowledge-Attitude-Practice
3 |  | Have rabies awareness campaigns, including responsible dog ownership, been expanded to more areas? | Intended audience and areas covered | 0 |  | Communication-plan | 5.4.16- dog-population-management
3 |  | Has veterinary and animal technician training been completed across most of country? |  | 0
3 |  | Has the dog population management strategy been implemented nationwide? |  | 0
4 |  | Have dog population management and responsible dog ownership campaigns been continued after the elimination of canine-mediated human rabies? |  | 0
5 |  | Have dog population management and responsible dog ownership campaigns been continued as part of the post-elimination strategy? |  | 0 |  | Guidelines-dog-population-management
* Dog Population Management
Dog population management: Dog population management (DPM) is a multifaceted concept which aims to improve the health and wellbeing of free-roaming dogs and reduce problems they may present, within which permanently reducing the size or turnover rate of a dog population may be a goal (International Companion Animal Management Coalition, 2007). This goes far beyond dog population control which refers to a program with the aim of reducing a dog population to a particular level and/or maintaining it at that level and/or managing it in order to meet a predetermined objective (OIE, 2015a). Whilst the former is usually practiced using humane approaches and long-term objectives, the latter has often utilized inhumane methods with short-sighted goals.
DPM may be enacted for numerous animal welfare, public health or safety reasons associated with dogs, including human bite injuries, secondary infections and death, the spread of rabies and other zoonoses, noise and faecal contamination of the environment, traffic accidents, negative publicity for the government or an impact on tourism (International Companion Animal Management Coalition, 2007; Arluke and Atema, 2015; OIE, 2015a; World Animal Protection, 2015). Therefore, DPM programs can have one or more goals depending on the specific situation, and will require a ‘One Health’ approach involving close collaboration between animal health, human health and environmental sectors. A DPM program with potential to improve animal, human and environmental health may increase motivation to tackle the issues and bring on board more stakeholders to support efforts. (From new paper under review: The Role of Dog Population Managementin Rabies Elimination – Current Tools andthe Need for Improvements. Taylor, LH et al)
S
T
P
O
-R
ocio-cultural
DOG POPULATION RELATED ISSUES

## IEC
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
1 | Public awareness | Has an assessment been done to determine what message should be communicated to the target audience at a local level? | Determine who the target audience is and what message is appropriate to them. For example, through focus groups or surveys. | 0 |  | Examples of KAP surveys
1 |  | Have the target audiences been identified at a local level (e.g. at-risk communities, dog owners, children)? |  | 0 |  | 4.2.3 Understanding who needs to be involved
1 |  | Has an IEC plan* been developed and implemented on a small scale? | Main messages and intended audiences (e.g. responsible dog ownership, rabies and bite prevention and management, and any other relevant messages for audiences such as dog owners, teachers, children, etc.) | 0 |  | Communication-plan | 5.4.7-Awareness-campaign
1 |  | Has broad public awareness messaging started at a national level? | To increase awareness about responsible dog ownership, rabies and bite prevention and management (through channels such as World Rabies Day, other health days, newspaper radio and television campaigns, and other channels) | 1 | During World Rabies Day 2015 & 2016 | World Rabies Day
2 |  | Has an IEC plan been implemented beyond a local level? | Main messages, intended audience and areas covered | 0
2 |  | Has the IEC plan been reviewed and updated? |  | 0 |  | Communication-plan
3 |  | Has the IEC plan been integrated into the national rabies strategy and implemented at national level? |  | 0
5 |  | Have awareness programmes focusing on the maintenance of freedom from dog and dog transmitted human rabies been implemented? | What are the main messages? Who is the intended audience? | 0
1 | Professional education | Has an assessment been undertaken to determine the training needs of the professionals at a local level? | For example: Did officials assess whether doctors can diagnose rabies? Did officials assess whether veterinarians can vaccinate dogs safely? | 0 |  | 5.3-Who-do-we-need-to-train
1 |  | Have human and animal health professionals involved in rabies control been identified at a local level? |  | 1
1 |  | Has a training plan been developed at a local level? |  | 0 |  | 5.5-What-are-we-going-to-do-human-component
1 |  | Have training or refresher courses on rabies and public communication been initiated for professionals in human and animal health at a local level? | Participant organisations/agencies | 0 |  | GARC Education Platform
2 |  | Has training of human and animal health personnel been conducted in most parts of the country? | Participant organisations/agencies | 1 | Training conducted for human health | 5.3-Who-do-we-need-to-train | GARC Education Platform
1 | Advocacy | Has an advocacy stakeholder analysis* been done at a local level and target audiences been identified? | For example, at-risk community leaders/authorities, politicians and other policy influencers and decision makers | 0 |  | Drafting an advocacy strategy | A toolkit for influencing policy
1 |  | Has an advocacy plan* been developed and implemented at a local level? |  | 0
2 |  | Have small-scale program successes been communicated to authorities/leaders in other parts of the country? | Main messages, audiences, areas covered | 0
2 |  | Has an advocacy stakeholder analysis* been done at a national level and have the target audiences been identified? |  | 0
2 |  | Has an advocacy campaign to national leaders/authorities been undertaken to ensure that a national rabies control strategy is created and properly resourced? | Main messages, audiences | 1
3 |  | Have human rabies free zones been declared publicly? | Areas covered | 0
4 |  | Has national freedom from dog-transmitted rabies been publically declared? |  | 0
4 |  | Has national freedom from canine-mediated human rabies been publically declared? |  | 0
* DEFINITIONS
| IEC Plan | A structured plan for Information, Education and Communication (IEC) that has agreed objectives, audiences, messages, channels and timelines to increase awareness of rabies prevention and control. (See Blueprint links in SARE tool for guidance on creating a plan.)
| Advocacy Plan | A structured plan to make rabies prevention and control a priority among leaders, decision-makers and policy influencers. (See Blueprint links in SARE tool for guidance on creating a plan.)
| Advocacy stakeholder analysis | Identification of the people and organisations who play a role in rabies prevention and control, and determination of the most effective ways to help make rabies a priority for them. (See Blueprint links in SARE tool for guidance on creating a plan.)
INFORMATION, EDUCATION, AND COMMUNICATION
S
T
P
O
-R
ocio-cultural

## Cross-cutting issues
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
0 | Intersectoral collaboration | Are the results of rabies sample(s) shared appropriately with local and national authorities? | Agencies involved | 1 |  | 6. Reporting of rabies data
1 |  | Have the main national stakeholders in rabies prevention and control been identified? | Agencies of stakeholders involved | 1 |  | 2. Roles-and-Responsibilities | Challenges of animal health information systems and surveillance for animal diseases and zoonoses
1 |  | Have stakeholder consultations been held within the last 3 years at the national level? |  | 0 |  | 2. Roles-and-Responsibilities
1 |  | Has an intersectoral rabies task force, committee or working group been established at a local or national level and do they meet at least twice a year? | Agencies of members of task force | 1 | The Rabies TWG meets monthly | 2. Roles-and-Responsibilities | Challenges of animal health information systems and surveillance for animal diseases and zoonoses
2 |  | Are mechanisms for regular intersectoral collaboration in place and are they implemented? |  | 0 |  | 2. Roles-and-Responsibilities
2 |  | Has the contribution and role of private sector been clarified and shared with other stakeholders? |  | 0 |  | 2. Roles-and-Responsibilities
1 | National programme and strategy | Based on a small-scale experience, has a short term rabies action plan been developed and endorsed by relevant stakeholders at local / national level? |  | 0 |  | 5.1-What-do-we-need-to-know-before | 1.8-What-measures-are-available | 2. Roles-and-Responsibilities
1 |  | Have mechanisms for mobilizing emergency funds in case of an outbreak been identified? |  | 0 |  | 3.3-Costs-and-Funding
2 |  | Has a national strategy for rabies prevention, control and eventual elimination been drafted, shared with all relevant stakeholders and finalised? |  | 0 |  | Components-of-a-successful-rabies-programme
2 |  | Have government resources been identified and allocated in support of the national rabies control strategy? |  | 0 |  | 3.3-Costs-and-Funding
3 |  | Has the national strategy been refined based on monitoring and evaluation? |  | 0 |  | 5.6-Evaluation | 5.7.1-Sustainability
4 |  | Have veterinary border inspection and quarantine measures been fully implemented in accordance with national regulations? |  | 0 |  | OIE Terrestrial Animal Health Code
CROSS-CUTTING ISSUES
O
S
P
T
-R
rganization

## Legislation
Instructions: Enter "0" under Status if No or None, or "1" if Yes
STAGE | subcomponent | ACHIEVEMENTS / ACTIVITIES | OTHER IMPORTANT INFORMATION (please include in REMARKS) | STATUS | REMARKS | Rabies Blueprint references and other links
0 | National case definition for animal rabies | Is a case definition available that is consistent with the OIE guidelines for animal rabies? |  | 1 |  | OIE Terrestrial Animal Health Code
1 |  | Do all of the relevant professionals know the case definition for animal rabies? | Agencies the case definition was disseminated to | 1 |  | OIE Terrestrial Animal Health Code
0 | National case definition for human rabies | Is a case definition available that is consistent with the WHO guidelines for human rabies? |  | 1 | There are standard and community case definitions for human rabies | WHO expert consultation on rabies
1 |  | Do all of the relevant professionals know the case definition for human rabies? | Agencies the case definition was disseminated to | 1 |  | WHO expert consultation on rabies
0 | Legal framework | Does the national authority report at least one confirmed rabies case to the WHO, OIE or PARACON? | Year of last reported rabies case | 0 |  | WHO Collaborating Centres and OIE Reference Laboratories
1 |  | Is there national legislation that is relevant to rabies prevention and control? | For example: an Animal act; compulsory vaccination, etc. Title of the framework and the year it was passed | 0 |  | 3.2. Legislation
1 |  | If there is legislation, has it been reviewed and endorsed? | Year the framework was reviewed | 0 |  | 3.2. Legislation
1 |  | Has rabies been made a notifiable disease in animals? |  | 1 |  | 3.2. Legislation | 3.2.3-Why-does-rabies-need-to-be-notifiable | OIE Terrestrial Animal Health Code | 3.2.9-How-to-make-rabies-notifiable
1 |  | Has rabies been made a notifiable disease in humans? |  | 1 | human rabies is one of the immediately reportable diseases in Liberia | 3.2. Legislation | 3.2.3-Why-does-rabies-need-to-be-notifiable | WHO expert consultation on rabies | 3.2.9-How-to-make-rabies-notifiable
1 |  | Is there legislation that includes the compulsory rabies vaccination of dogs or has it been proposed if it is not already in place? |  | 0
1 |  | Does legislation include measures for rabies outbreak response? |  | 0
2 |  | Has legislation been updated to include specifications on the compulsory vaccination of dogs and the international movement of animals? |  | 0 |  | General-guide-on-veterinary legislation | 3.2.11- laws-and-by-laws
3 |  | Is the relevant legislation enforced at the national level? |  | 0
LEGISLATION
P
S
O
T
-R
olitical

## S0-S5 (hidden)
LEGISLATION | DATA COLLECTION AND ANALYSIS | LABORATORY DIAGNOSIS | INFORMATION, EDUCATION AND COMMUNICATION | PREVENTION AND CONTROL | DOG POPULATION RELATED ISSUES | CROSS CUTTING ISSUES | STAGE LEGEND
[7 empty] | 0 | 1 | 2 | 3 | 4 | 5
A case definition consistent with OIE for animal rabies is available | Reporting of dog rabies from local to national level | Contacts with an international rabies reference laboratory or international collaborating/reference center are established | Communications situation and needs (KAP, training needs, stakeholder analysis) assessed at pilot level | Vaccines for human rabies prophylaxis are available in the country | Dog population studies to determine size, turn-over and accessibility have been conducted in pilot areas | Result of rabies sample(s) are shared appropriately with local and national authorities
A case definition consistent with WHO for human rabies is available | Reporting of human rabies from local to national level | At least one rabies suspect sample of animals or humans is submitted to an international rabies reference laboratory for confirmation | Target audiences identified for public, professional and advocacy communications (at-risk communities, dog owners, health professionals, at-risk community leaders/authorities, politicians) | A first assessment on access to PEP (and PreP) has been carried out | Other rabies control activities such as IBCM, dog population management have been implemented (at least in pilot areas) | Identification of main national stakeholders in rabies prevention and control has been carried out
The national authority reports at least one confirmed rabies case to WHO or OIE | Dog rabies data analysis capacity at the national level has been established | Several rabies suspect samples of animals or humans are submitted to a national laboratory and analysed by an internationally recommended method | A rabies communication plan developed for public, professional and advocacy target audiences | Dog rabies vaccines are available in the country | Rabies awareness campaigns including responsible dog ownership have been expanded to more areas | Stakeholder consultations held within the last 3 years
The animal rabies case definition has been disseminated to relevant professionals | Human rabies data analysis capacity at the national level has been established | Rabies diagnostic capacity has been established in at least one national laboratory | Public awareness activities on rabies prevention, dog bite management and dog vaccination initiated (e.g. WRD) | Dog vaccination is initiated in some parts or pilot areas of the country | Refinement of strategy based on current dog ecology and KAP surveys | Intersectoral rabies task force, committee or working group established at local or national level and meeting at least twice a year
The human rabies case definition has been disseminated to relevant professionals | Dog bite reporting and documentation have been reviewed and data compiled | Routine laboratory diagnosis of animal rabies cases in country | Training or refresher courses on rabies initiated for professionals in human and animal health | Other rabies control activities such as IBCM, dog population management have been implemented (at least in pilot areas) | Dog population management and responsible dog ownership campaigns are continued | Based on pilot area experience, a short term rabies action plan has been developed and endorsed by relevant stakeholders at local / national level
There is a legal framework relevant to rabies prevention and control | Dog population studies to determine size, turn-over and accessibility have been conducted in pilot areas | Capacity for sample collection and transportation has been established | Information on the epidemiology of rabies is regularly shared with all stakeholders | WHO pre-qualified human rabies vaccines available and accessible in most parts of the country |  | Mechanisms for mobilizing emergency funds in case of an outbreak have been identified
If there is a legal framework, the framework has been reviewed to determine if it is adequate. | Establishment of linked human and animal rabies surveillance systems, including agreed SOPs | Access to laboratory diagnosis is available throughout the country for animal samples (and if possible also for human samples) | Rabies communication plan reviewed and updated | Any use of human biologics not WHO-pre-qualified is being phased out (e.g. nerve tissue vaccines, low quality vaccines) |  | Mechanisms for regular intersectoral collaboration are in place and implemented
Rabies is made a notifiable disease in animals | Human rabies surveillance systems, including feedback mechanism, coordinated between administrative levels (national, province, district, municipal, etc.) | Regular characterization and analysis of circulating rabies virus variants by a national or international laboratory | Rabies awareness campaigns including responsible dog ownership have been expanded to more areas | Supply and access to WHO pre-qualified human rabies vaccines for PrEP for professionals at risk ensured throughout the pilot areas |  | Contribution and role of private sector clarified and shared with other stakeholders
Rabies is made a notifiable disease in humans | Animal rabies surveillance systems, including feedback mechanism, coordinated between administrative levels (national, province, district, municipal, etc.) | Maintenance of existing surveillance activities, including ongoing laboratory investigation, for all suspected cases in dogs in the country | Public awareness and sensitization campaigns are tailored to specific target groups (e.g. community leaders, authorities and health professionals, World Rabies Day Activities). | Only quality dog vaccines in accordance with OIE standards are being used |  | A national strategy and programme for rabies prevention, control and eventual elimination has been drafted and shared with all relevant stakeholders
Legislation includes compulsory rabies vaccination of dogs or proposed if not in place | Information on the epidemiology of rabies is regularly shared with all stakeholders | Epidemiological data from routine surveillance of all animals (working animals, livestock and wildlife) used to refine the national rabies strategy | Training of human and animal health personnel has been conducted in most parts of the country | Dog vaccination campaigns are regularly implemented in response to human cases and animal outbreaks |  | Government resources identified and allocated in support of the national rabies control strategy and programme
Legislation includes measures for outbreak response | Conduct field investigations for all suspected human rabies cases | On-going laboratory investigation of all suspected cases in domestic and wild animal species in the country | Communication plan on rabies elimination is implemented | IBCM SOPs agreed, including sharing of information between sectors |  | Refinement of national strategy based on monitoring and evaluation
The animal rabies case definition has been reviewed and endorsed (intersectoral approach) | Epidemiological evidence available to rule out dog- transmitted human rabies cases |  | Declaration of dog-transmitted rabies free zones publicized | SOPs for the observation of dogs involved in biting incidents available |  | Veterinary border inspection and quarantine measures are fully implemented in accordance with national regulations
The human rabies case definition has been reviewed and endorsed (intersectoral approach) | Conduct field investigations and laboratory confirmation for all suspected rabies outbreaks in dogs |  | Promote responsible dog ownership together with rabies awareness campaigns | WHO pre-qualified Pre- and Post- Exposure Prophylaxis available and accessible to high risk and exposed individuals throughout the country
Legal frameworks updated to include specifications on compulsory vaccination of dogs and international movement of animals. | Initiate collection of local or national health economic data on rabies control to make the case for rabies control investment |  | Strengthen public awareness campaigns to advocate dog vaccination to leaders and authorities | Mass dog vaccination campaigns (at least 70% of the total dog population) are conducted according to the national rabies strategy
Declaration of national dog-transmitted rabies freedom publicized | Expand health economic studies to support further prioritization within the national rabies control programme |  | Declaration of national dog-transmitted rabies freedom publicized | Post-vaccination surveys in dogs to evaluate vaccination coverage
| Maintenance of existing surveillance activities for all suspected cases in humans in the country |  | Awareness programmes focusing on maintenance of freedom from dog and dog transmitted human rabies | Capacity to conduct field investigations and planned outbreak response for animal and human rabies cases is available in the entire country
| Epidemiological data from routine surveillance of all animals (working animals, livestock and wildlife) used to refine the national rabies strategy |  | Dog population management and responsible dog ownership campaigns are continued | Sufficient facilities for observation of rabies-suspected dogs established and comply with international animal welfare regulations
| On-going surveillance system for rabies maintained |  |  | Identification of potential rabies free zones where canine variant cases is absent for at least a 2 year period
Dog vaccination campaigns are maintained in zones where dog rabies is still present or where otherwise justified (e.g. risk of introduction)
Freedom from dog-transmitted rabies in the entire country verified by the absence of canine variant cases for at least a 2 year period
Measures to prevent re-introduction applied in designated rabies free zones including dialogue with neighbouring countries.
Emergency response/contingency plan to any case of animal rabies involving a canine variant developed in preparation of the post elimination phase
Modified protocols for PEP administration for rabies free areas implemented
Based on risk assessment, dog vaccination campaigns are maintained where justified
Capacity for outbreak and re-introduction response maintained

## masterlist (hidden)
# | STAGE | COMPONENT | ACTIVITY | KEY | COUNTRY STATUS | COUNTRY NOTES
49 | 0 | LAB | Have contacts with an international rabies reference laboratory or international collaborating/reference center been established? | KEY | 1 | FAO Reference Lab, PADOVA, Rome, Italy
50 | 0 | LAB | Has at least one human or animal rabies suspect sample been submitted to an international rabies reference laboratory for confirmation? | KEY | 1 | 2017 to FAO reference Lab
96 | 0 | CCI | Are the results of rabies sample(s) shared appropriately with local and national authorities? |  | 1 | 0
108 | 0 | LEG | Is a case definition available that is consistent with the OIE guidelines for animal rabies? |  | 1 | 0
110 | 0 | LEG | Is a case definition available that is consistent with the WHO guidelines for human rabies? |  | 1 | There are standard and community case definitions for human rabies
112 | 0 | LEG | Does the national authority report at least one confirmed rabies case to the WHO, OIE or PARACON? | KEY | 0 | 0
1 | 1 | DCA | Are dog rabies cases reported from a local to the national level? | KEY | 0 | There is no structure in place for reporting dog rabies cases in the animal health sector
2 | 1 | DCA | Are human rabies cases reported from a local to the national level? | KEY | 1 | There's an existing reporting structure of human rabies cases from local to national levels using the IDSR guidelines
3 | 1 | DCA | Are all human or animal rabies testing results being reported to a relevant international database such as WHO, OIE or PARACON? |  | 0 | 0
4 | 1 | DCA | Is there capacity to analyze dog rabies data at the national level? |  | 0 | 0
5 | 1 | DCA | Is there capacity to analyze human rabies data at the national level? |  | 1 | 0
6 | 1 | DCA | Has an animal rabies surveillance* system been established at the national level? |  | 0 | The process to establish a surveillance system is ongoing with full support from FAO
7 | 1 | DCA | Has a human rabies surveillance* system been established at the national level? |  | 1 | There is functional surveillance system established at all levels with surveillance focal persons
8 | 1 | DCA | Have reports on the number of humans bitten by dogs been compiled and reviewed? |  | 1 | its compliled, reviewed and placed in the weekly Epi bullettin
9 | 1 | DCA | Have dog population studies and KAP surveys been conducted to determine size, turn-over and accessibility of dogs for vaccination on a small scale? |  | 0 | 0
23 | 1 | PCO | Are vaccines for human rabies prophylaxis available in one or more parts of the country? | KEY | 1 | Available in all parts of the country
24 | 1 | PCO | Has the supply and access to WHO pre-qualified human rabies vaccines for PrEP for professionals at risk been ensured in local areas? | KEY | 0 | 0
30 | 1 | PCO | Are dog rabies vaccines available in at least one location in the country? | KEY | 0 | 0
31 | 1 | PCO | Has dog vaccination been initiated in some parts of the country? |  | 0 | 0
38 | 1 | PCO | Has Integrated Bite Case Management (IBCM)* been implemented at a local level? |  | 0 | 0
39 | 1 | PCO | Have Standard Operating Procedures (SOPs) for coordinated action on reported outbreaks* been established? |  | 0 | 0
51 | 1 | LAB | Is there capacity to conduct rabies diagnosis in at least one national laboratory (veterinary or medical laboratory)? | KEY | 1 | Central Veterinary Laboratory has the capacity to conduct rabies diagnosis, but needs strengthening
52 | 1 | LAB | Have several rabies suspect samples of animals or humans been submitted to a national laboratory and analysed? |  | 1 | Central Veterinary Laboratory
53 | 1 | LAB | Is animal rabies diagnosis conducted in at least one national laboratory? |  | 1 | 0
54 | 1 | LAB | Are rabies suspect samples of animals or humans submitted twice yearly to an international laboratory and analysed? |  | 0 | 0
62 | 1 | DPM | Have discussions been held with stakeholders to create a dog population management strategy at a local level? |  | 1 | discussions have been held among stakeholders
63 | 1 | DPM | Have you involved officials in waste management in your stakeholder meetings |  | 1 | Environmental Protenction Agency, City Corporations
75 | 1 | IEC | Has an assessment been done to determine what message should be communicated to the target audience at a local level? |  | 0 | 0
76 | 1 | IEC | Have the target audiences been identified at a local level (e.g. at-risk communities, dog owners, children)? |  | 0 | 0
77 | 1 | IEC | Has an IEC plan* been developed and implemented on a small scale? | KEY | 0 | 0
78 | 1 | IEC | Has broad public awareness messaging started at a national level? |  | 1 | During World Rabies Day 2015 & 2016
83 | 1 | IEC | Has an assessment been undertaken to determine the training needs of the professionals at a local level? |  | 0 | 0
84 | 1 | IEC | Have human and animal health professionals involved in rabies control been identified at a local level? |  | 1 | 0
85 | 1 | IEC | Has a training plan been developed at a local level? |  | 0 | 0
86 | 1 | IEC | Have training or refresher courses on rabies and public communication been initiated for professionals in human and animal health at a local level? |  | 0 | 0
88 | 1 | IEC | Has an advocacy stakeholder analysis* been done at a local level and target audiences been identified? |  | 0 | 0
89 | 1 | IEC | Has an advocacy plan* been developed and implemented at a local level? |  | 0 | 0
97 | 1 | CCI | Have the main national stakeholders in rabies prevention and control been identified? |  | 1 | 0
98 | 1 | CCI | Have stakeholder consultations been held within the last 3 years at the national level? |  | 0 | 0
99 | 1 | CCI | Has an intersectoral rabies task force, committee or working group been established at a local or national level and do they meet at least twice a year? | KEY | 1 | The Rabies TWG meets monthly
102 | 1 | CCI | Based on a small-scale experience, has a short term rabies action plan been developed and endorsed by relevant stakeholders at local / national level? | KEY | 0 | 0
103 | 1 | CCI | Have mechanisms for mobilizing emergency funds in case of an outbreak been identified? |  | 0 | 0
109 | 1 | LEG | Do all of the relevant professionals know the case definition for animal rabies? |  | 1 | 0
111 | 1 | LEG | Do all of the relevant professionals know the case definition for human rabies? |  | 1 | 0
113 | 1 | LEG | Is there national legislation that is relevant to rabies prevention and control? |  | 0 | 0
114 | 1 | LEG | If there is legislation, has it been reviewed and endorsed? |  | 0 | 0
115 | 1 | LEG | Has rabies been made a notifiable disease in animals? | KEY | 1 | 0
116 | 1 | LEG | Has rabies been made a notifiable disease in humans? | KEY | 1 | human rabies is one of the immediately reportable diseases in Liberia
117 | 1 | LEG | Is there legislation that includes the compulsory rabies vaccination of dogs or has it been proposed if it is not already in place? | KEY | 0 | 0
118 | 1 | LEG | Does legislation include measures for rabies outbreak response? |  | 0 | 0
10 | 2 | DCA | Have linked human and animal rabies surveillance systems, including agreed SOPs, been established? |  | 0 | 0
11 | 2 | DCA | Are human rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? |  | 1 | 0
12 | 2 | DCA | Are animal rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? |  | 0 | establishment of system in progress
13 | 2 | DCA | Is information on the epidemiology of rabies regularly shared with all stakeholders? | KEY | 1 | Information on dog bite cases are shared with stakeholders using the human health Epi Bullettin
14 | 2 | DCA | Is the on-going surveillance system for rabies being maintained? | KEY | 1 | For human health
25 | 2 | PCO | Has an assessment* been done to determine the availability and access to PEP (and PreP)? |  | 0 | 0
26 | 2 | PCO | Are WHO pre-qualified human rabies vaccines available and accessible in most parts of the country? | KEY | 1 | 0
27 | 2 | PCO | Are any human biologics that are not WHO-pre-qualified being phased out? (e.g. nerve tissue vaccines, low quality vaccines) |  | 1 | 0
32 | 2 | PCO | Are only quality dog vaccines in accordance with OIE standards being used? |  | 0 | 0
33 | 2 | PCO | Are dog vaccination campaigns regularly implemented in response to human cases and animal outbreaks? | KEY | 0 | 0
40 | 2 | PCO | Have IBCM SOPs, including sharing of information between sectors, been agreed upon? |  | 0 | 0
41 | 2 | PCO | Are SOPs available for the observation of dogs involved in biting incidents? |  | 0 | 0
42 | 2 | PCO | Have facilities or protocols been established for the observation of rabies-suspected dogs? |  | 0 | 0
55 | 2 | LAB | Is there regular laboratory diagnosis of animal rabies cases in country? |  | 0 | not regular
56 | 2 | LAB | Has capacity for regular sample collection and transportation been established and functioning? |  | 0 | 0
64 | 2 | DPM | Has a DPM* strategy and programmebeen drafted and shared with all relevant stakeholders at a local level? |  | 0 | 0
65 | 2 | DPM | Has the DPM strategy been finalized? |  | 0 | 0
66 | 2 | DPM | Has public sensitisation about DPM been built into rabies awareness campaigns at a local level? |  | 0 | 0
67 | 2 | DPM | Has dog population management been implemented at a local level? |  | 0 | 0
68 | 2 | DPM | Have training or refresher courses on animal handling and sterilisation been initiated for professionals in animal health at a local level? |  | 0 | 0
79 | 2 | IEC | Has an IEC plan been implemented beyond a local level? |  | 0 | 0
80 | 2 | IEC | Has the IEC plan been reviewed and updated? |  | 0 | 0
87 | 2 | IEC | Has training of human and animal health personnel been conducted in most parts of the country? |  | 1 | Training conducted for human health
90 | 2 | IEC | Have small-scale program successes been communicated to authorities/leaders in other parts of the country? |  | 0 | 0
91 | 2 | IEC | Has an advocacy stakeholder analysis* been done at a national level and have the target audiences been identified? |  | 0 | 0
92 | 2 | IEC | Has an advocacy campaign to national leaders/authorities been undertaken to ensure that a national rabies control strategy is created and properly resourced? | KEY | 1 | 0
100 | 2 | CCI | Are mechanisms for regular intersectoral collaboration in place and are they implemented? |  | 0 | 0
101 | 2 | CCI | Has the contribution and role of private sector been clarified and shared with other stakeholders? |  | 0 | 0
104 | 2 | CCI | Has a national strategy for rabies prevention, control and eventual elimination been drafted, shared with all relevant stakeholders and finalised? | KEY | 0 | 0
105 | 2 | CCI | Have government resources been identified and allocated in support of the national rabies control strategy? | KEY | 0 | 0
119 | 2 | LEG | Has legislation been updated to include specifications on the compulsory vaccination of dogs and the international movement of animals? | KEY | 0 | 0
15 | 3 | DCA | Have field investigations for all suspected human rabies cases been conducted? | KEY | 0 | Not for all cases
16 | 3 | DCA | Is epidemiological evidence available to rule out dog-transmitted human rabies cases? | KEY | 0 | 0
17 | 3 | DCA | Has an advocacy plan been approved by the government for local level implementation? |  | 0 | 0
18 | 3 | DCA | Are field investigations and laboratory confirmations conducted for all suspected rabies outbreaks in dogs? | KEY | 0 | 0
21 | 3 | DCA | Has the collection of local or national health economic and/or other disease prioritization tool data* on rabies control been initiated to make the case for rabies control investment? |  | 0 | 0
22 | 3 | DCA | Have the health economic data and/or other disease prioritization tool analyses been expanded to support further prioritization within the national rabies control programme? |  | 0 | 0
28 | 3 | PCO | Is WHO pre-qualified Pre- and Post- Exposure Prophylaxis available and accessible to high risk and exposed individuals throughout the country? | KEY | 1 | 0
34 | 3 | PCO | Are mass dog vaccination campaigns reaching at least 70% of the total dog population conducted according to the national rabies strategy? | KEY | 0 | 0
35 | 3 | PCO | Are post-vaccination surveys* in dogs being carried out to evaluate vaccination coverage? | KEY | 0 | 0
43 | 3 | PCO | Is there capacity to conduct field investigations and planned outbreak responses for animal and human rabies cases in the entire country? |  | 1 | limited capacities
44 | 3 | PCO | Have potential rabies-free zones been identified where canine variant cases have been absent for at least a 2 year period? | KEY | 0 | 0
45 | 3 | PCO | Has dialogue been initiated with neighbouring countries to prevent the re-introduction of rabies into designated rabies-free zones? |  | 0 | 0
57 | 3 | LAB | Are wildlife samples submitted for rabies laboratory diagnosis? |  | 0 | 0
58 | 3 | LAB | Is access to reliable laboratory diagnosis available throughout the country for animal samples (and if possible also for human and wildlife samples)? |  | 0 | 0
59 | 3 | LAB | Is there regular characterization and analysis of circulating rabies virus variants by a national or international laboratory? |  | 0 | 0
69 | 3 | DPM | Has the DPM strategy been assessed and refined based on current dog ecology or KAP surveys? |  | 0 | 0
70 | 3 | DPM | Have rabies awareness campaigns, including responsible dog ownership, been expanded to more areas? |  | 0 | 0
71 | 3 | DPM | Has veterinary and animal technician training been completed across most of country? |  | 0 | 0
72 | 3 | DPM | Has the dog population management strategy been implemented nationwide? |  | 0 | 0
81 | 3 | IEC | Has the IEC plan been integrated into the national rabies strategy and implemented at national level? | KEY | 0 | 0
93 | 3 | IEC | Have human rabies free zones been declared publicly? | KEY | 0 | 0
106 | 3 | CCI | Has the national strategy been refined based on monitoring and evaluation? |  | 0 | 0
120 | 3 | LEG | Is the relevant legislation enforced at the national level? |  | 0 | 0
19 | 4 | DCA | Are existing surveillance activities for all suspected cases in humans maintained in the country? | KEY | 0 | 0
20 | 4 | DCA | Has the epidemiological data from the routine surveillance of all animals (working animals, livestock and wildlife) been used to refine the national rabies strategy? | KEY | 0 | 0
36 | 4 | PCO | Are dog vaccination campaigns maintained in zones where dog rabies is still present or where otherwise justified (e.g. risk of introduction)? | KEY | 0 | 0
46 | 4 | PCO | Has freedom from dog-transmitted rabies in the entire country been verified by the absence of canine variant cases for at least a 2 year period? | KEY | 0 | 0
47 | 4 | PCO | Has an emergency response/contingency plan been developed to address any reintroduced case of animal rabies involving a canine variant? | KEY | 0 | 0
60 | 4 | LAB | Is there maintenance of existing surveillance activities, including ongoing laboratory investigation, for all suspected cases in dogs in the country? | KEY | 0 | 0
73 | 4 | DPM | Have dog population management and responsible dog ownership campaigns been continued after the elimination of canine-mediated human rabies? |  | 0 | 0
94 | 4 | IEC | Has national freedom from dog-transmitted rabies been publically declared? | KEY | 0 | 0
95 | 4 | IEC | Has national freedom from canine-mediated human rabies been publically declared? |  | 0 | 0
107 | 4 | CCI | Have veterinary border inspection and quarantine measures been fully implemented in accordance with national regulations? |  | 0 | 0
29 | 5 | PCO | Have modified protocols for PEP administration for rabies-free areas been implemented? | KEY | 0 | 0
37 | 5 | PCO | Based on risk assessments, are dog vaccination campaigns being maintained where justified? | KEY | 0 | 0
48 | 5 | PCO | Has the capacity for outbreak and re-introduction response been maintained? | KEY | 0 | 0
61 | 5 | LAB | Are there on-going laboratory investigations of all suspected cases in domestic and wild animal species in the country? | KEY | 0 | 0
74 | 5 | DPM | Have dog population management and responsible dog ownership campaigns been continued as part of the post-elimination strategy? | KEY | 0 | 0
82 | 5 | IEC | Have awareness programmes focusing on the maintenance of freedom from dog and dog transmitted human rabies been implemented? | KEY | 0 | 0

## SUMMARY (Score)
Stepwise Approach towards Rabies Elimination - Liberia , 2017
STAGE 0.5
ACTIVITY SUMMARY |  |  | STAGE SUMMARY
COMPONENTS | PENDING ACTIVITIES | ACCOMPLISHED ACTIVITIES | STAGE* |  | PENDING ACTIVITIES | ACCOMPLISHED ACTIVITIES | CRITICAL ACTIVITIES ACCOMPLISHED | STAGE COMPLETED?
[13 empty] | 0% | 0
Data collection and analysis Total number of activities = 22 | 15 | 7 | 0 | Total number of activities = 6 | 1 | 5 | 2 | COMPLETED
| IIIIIIIIIIIIIII | IIIIIII | 0.5 |  | I | IIIII |  | PENDING |  |  |  |  | 0% | 0
Prevention and Control Total number of activities = 26 | 21 | 5 | 1 | Total number of activities = 44 | 26 | 18 | 6 | COMPLETED
| IIIIIIIIIIIIIIIIIIIII | IIIII | 1.5 |  | IIIIIIIIIIIIIIIIIIIIIIIIII | IIIIIIIIIIIIIIIIII |  | PENDING |  |  |  | 8% | 2
Laboratory diagnosis Total number of activities = 13 | 8 | 5 | 2 | Total number of activities = 31 | 24 | 7 | 4 | COMPLETED
| IIIIIIII | IIIII | 2.5 |  | IIIIIIIIIIIIIIIIIIIIIIII | IIIIIII |  | PENDING |  |  | 22% | 7
Dog population related issues Total number of activities = 13 | 11 | 2 | 3 | Total number of activities = 23 | 21 | 2 | 1 | PENDING
| IIIIIIIIIII | II | 3.5 |  | IIIIIIIIIIIIIIIIIIIII | II |  | PENDING |  | 40% | 18
Information, Education, Communication Total number of activities = 21 | 17 | 4 | 4 | Total number of activities = 10 | 10 | 0 | 0 | PENDING
| IIIIIIIIIIIIIIIII | IIII | 4.5 |  | IIIIIIIIII |  |  | PENDING | 83% | 5
Cross-cutting issues Total number of activities = 12 | 9 | 3 | 5 | Total number of activities = 6 | 6 | 0 | 0 | PENDING
| IIIIIIIII | III |  |  | IIIIII
Legislation Total number of activities = 13 | 7 | 6 | 5 |  |  |  |  | PENDING
| IIIIIII | IIIIII | * Scores in increments of 0.5 show progress along a particular stage.
COUNTRY PROGRESS

## SUMMARY (S0-S5)
Stepwise Approach towards Rabies Elimination |  |  |  | LIBERIA |  | 2017
SUMMARY OF RABIES PROGRAM ACTIVITIES
STAGE | DATA COLLECTION & ANALYSIS |  | PREVENTION & CONTROL |  | LABORATORY DIAGNOSIS |  | DOG POPULATION RELATED ISSUES |  | INFORMATION, EDUCATION, COMMUNICATION |  | CROSS-CUTTING ISSUES |  | LEGISLATION
| Pending | Accomplished | Pending | Accomplished | Pending | Accomplished | Pending | Accomplished | Pending | Accomplished | Pending | Accomplished | Pending | Accomplished
0 | [5 empty] | Have contacts with an international rabies reference laboratory or international collaborating/reference center been established? | [5 empty] | Are the results of rabies sample(s) shared appropriately with local and national authorities? |  | Is a case definition available that is consistent with the OIE guidelines for animal rabies?
[6 empty] | Has at least one human or animal rabies suspect sample been submitted to an international rabies reference laboratory for confirmation? | [7 empty] | Is a case definition available that is consistent with the WHO guidelines for human rabies?
Does the national authority report at least one confirmed rabies case to the WHO, OIE or PARACON?
1 | Are dog rabies cases reported from a local to the national level? |  |  | Are vaccines for human rabies prophylaxis available in one or more parts of the country? |  | Is there capacity to conduct rabies diagnosis in at least one national laboratory (veterinary or medical laboratory)? |  | Have discussions been held with stakeholders to create a dog population management strategy at a local level? | Has an assessment been done to determine what message should be communicated to the target audience at a local level? |  |  | Have the main national stakeholders in rabies prevention and control been identified? |  | Do all of the relevant professionals know the case definition for animal rabies?
|  | Are human rabies cases reported from a local to the national level? | Has the supply and access to WHO pre-qualified human rabies vaccines for PrEP for professionals at risk been ensured in local areas? |  |  | Have several rabies suspect samples of animals or humans been submitted to a national laboratory and analysed? |  | Have you involved officials in waste management in your stakeholder meetings | Have the target audiences been identified at a local level (e.g. at-risk communities, dog owners, children)? |  | Have stakeholder consultations been held within the last 3 years at the national level? |  |  | Do all of the relevant professionals know the case definition for human rabies?
| Are all human or animal rabies testing results being reported to a relevant international database such as WHO, OIE or PARACON? |  | Are dog rabies vaccines available in at least one location in the country? |  |  | Is animal rabies diagnosis conducted in at least one national laboratory? |  |  | Has an IEC plan* been developed and implemented on a small scale? |  |  | Has an intersectoral rabies task force, committee or working group been established at a local or national level and do they meet at least twice a year? | Is there national legislation that is relevant to rabies prevention and control?
| Is there capacity to analyze dog rabies data at the national level? |  | Has dog vaccination been initiated in some parts of the country? |  | Are rabies suspect samples of animals or humans submitted twice yearly to an international laboratory and analysed? |  |  |  |  | Has broad public awareness messaging started at a national level? | Based on a small-scale experience, has a short term rabies action plan been developed and endorsed by relevant stakeholders at local / national level? |  | If there is legislation, has it been reviewed and endorsed?
|  | Is there capacity to analyze human rabies data at the national level? | Has Integrated Bite Case Management (IBCM)* been implemented at a local level? | [5 empty] | Has an assessment been undertaken to determine the training needs of the professionals at a local level? |  | Have mechanisms for mobilizing emergency funds in case of an outbreak been identified? |  |  | Has rabies been made a notifiable disease in animals?
| Has an animal rabies surveillance* system been established at the national level? |  | Have Standard Operating Procedures (SOPs) for coordinated action on reported outbreaks* been established? | [6 empty] | Have human and animal health professionals involved in rabies control been identified at a local level? |  |  |  | Has rabies been made a notifiable disease in humans?
|  | Has a human rabies surveillance* system been established at the national level? | [6 empty] | Has a training plan been developed at a local level? |  |  |  | Is there legislation that includes the compulsory rabies vaccination of dogs or has it been proposed if it is not already in place?
|  | Have reports on the number of humans bitten by dogs been compiled and reviewed? | [6 empty] | Have training or refresher courses on rabies and public communication been initiated for professionals in human and animal health at a local level? |  |  |  | Does legislation include measures for rabies outbreak response?
| Have dog population studies and KAP surveys been conducted to determine size, turn-over and accessibility of dogs for vaccination on a small scale? | [7 empty] | Has an advocacy stakeholder analysis* been done at a local level and target audiences been identified?
Has an advocacy plan* been developed and implemented at a local level?
2 | Have linked human and animal rabies surveillance systems, including agreed SOPs, been established? |  | Has an assessment* been done to determine the availability and access to PEP (and PreP)? |  | Is there regular laboratory diagnosis of animal rabies cases in country? |  | Has a DPM* strategy and programmebeen drafted and shared with all relevant stakeholders at a local level? |  | Has an IEC plan been implemented beyond a local level? |  | Are mechanisms for regular intersectoral collaboration in place and are they implemented? |  | Has legislation been updated to include specifications on the compulsory vaccination of dogs and the international movement of animals?
|  | Are human rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? |  | Are WHO pre-qualified human rabies vaccines available and accessible in most parts of the country? | Has capacity for regular sample collection and transportation been established and functioning? |  | Has the DPM strategy been finalized? |  | Has the IEC plan been reviewed and updated? |  | Has the contribution and role of private sector been clarified and shared with other stakeholders?
| Are animal rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? |  |  | Are any human biologics that are not WHO-pre-qualified being phased out? (e.g. nerve tissue vaccines, low quality vaccines) |  |  | Has public sensitisation about DPM been built into rabies awareness campaigns at a local level? |  |  | Has training of human and animal health personnel been conducted in most parts of the country? | Has a national strategy for rabies prevention, control and eventual elimination been drafted, shared with all relevant stakeholders and finalised?
|  | Is information on the epidemiology of rabies regularly shared with all stakeholders? | Are only quality dog vaccines in accordance with OIE standards being used? |  |  |  | Has dog population management been implemented at a local level? |  | Have small-scale program successes been communicated to authorities/leaders in other parts of the country? |  | Have government resources been identified and allocated in support of the national rabies control strategy?
|  | Is the on-going surveillance system for rabies being maintained? | Are dog vaccination campaigns regularly implemented in response to human cases and animal outbreaks? |  |  |  | Have training or refresher courses on animal handling and sterilisation been initiated for professionals in animal health at a local level? |  | Has an advocacy stakeholder analysis* been done at a national level and have the target audiences been identified?
|  |  | Have IBCM SOPs, including sharing of information between sectors, been agreed upon? | [6 empty] | Has an advocacy campaign to national leaders/authorities been undertaken to ensure that a national rabies control strategy is created and properly resourced?
Are SOPs available for the observation of dogs involved in biting incidents?
Have facilities or protocols been established for the observation of rabies-suspected dogs?
3 | Have field investigations for all suspected human rabies cases been conducted? |  |  | Is WHO pre-qualified Pre- and Post- Exposure Prophylaxis available and accessible to high risk and exposed individuals throughout the country? | Are wildlife samples submitted for rabies laboratory diagnosis? |  | Has the DPM strategy been assessed and refined based on current dog ecology or KAP surveys? |  | Has the IEC plan been integrated into the national rabies strategy and implemented at national level? |  | Has the national strategy been refined based on monitoring and evaluation? |  | Is the relevant legislation enforced at the national level?
| Is epidemiological evidence available to rule out dog-transmitted human rabies cases? |  | Are mass dog vaccination campaigns reaching at least 70% of the total dog population conducted according to the national rabies strategy? |  | Is access to reliable laboratory diagnosis available throughout the country for animal samples (and if possible also for human and wildlife samples)? |  | Have rabies awareness campaigns, including responsible dog ownership, been expanded to more areas? |  | Have human rabies free zones been declared publicly?
| Has an advocacy plan been approved by the government for local level implementation? |  | Are post-vaccination surveys* in dogs being carried out to evaluate vaccination coverage? |  | Is there regular characterization and analysis of circulating rabies virus variants by a national or international laboratory? |  | Has veterinary and animal technician training been completed across most of country?
| Are field investigations and laboratory confirmations conducted for all suspected rabies outbreaks in dogs? |  |  | Is there capacity to conduct field investigations and planned outbreak responses for animal and human rabies cases in the entire country? |  |  | Has the dog population management strategy been implemented nationwide?
| Has the collection of local or national health economic and/or other disease prioritization tool data* on rabies control been initiated to make the case for rabies control investment? |  | Have potential rabies-free zones been identified where canine variant cases have been absent for at least a 2 year period?
| Have the health economic data and/or other disease prioritization tool analyses been expanded to support further prioritization within the national rabies control programme? |  | Has dialogue been initiated with neighbouring countries to prevent the re-introduction of rabies into designated rabies-free zones?
4 | Are existing surveillance activities for all suspected cases in humans maintained in the country? |  | Are dog vaccination campaigns maintained in zones where dog rabies is still present or where otherwise justified (e.g. risk of introduction)? |  | Is there maintenance of existing surveillance activities, including ongoing laboratory investigation, for all suspected cases in dogs in the country? |  | Have dog population management and responsible dog ownership campaigns been continued after the elimination of canine-mediated human rabies? |  | Has national freedom from dog-transmitted rabies been publically declared? |  | Have veterinary border inspection and quarantine measures been fully implemented in accordance with national regulations?
| Has the epidemiological data from the routine surveillance of all animals (working animals, livestock and wildlife) been used to refine the national rabies strategy? |  | Has freedom from dog-transmitted rabies in the entire country been verified by the absence of canine variant cases for at least a 2 year period? | [5 empty] | Has national freedom from canine-mediated human rabies been publically declared?
Has an emergency response/contingency plan been developed to address any reintroduced case of animal rabies involving a canine variant?
5 |  |  | Have modified protocols for PEP administration for rabies-free areas been implemented? |  | Are there on-going laboratory investigations of all suspected cases in domestic and wild animal species in the country? |  | Have dog population management and responsible dog ownership campaigns been continued as part of the post-elimination strategy? |  | Have awareness programmes focusing on the maintenance of freedom from dog and dog transmitted human rabies been implemented?
Based on risk assessments, are dog vaccination campaigns being maintained where justified?
Has the capacity for outbreak and re-introduction response been maintained?

## PRIORITISATION
COUNTRY STATUS | Stepwise Approach towards Rabies Elimination |  |  | LIBERIA | 2017
0 | PRIORITISATION OF RABIES PROGRAM ACTIVITIES
STAGE | COMPONENT | ACTIVITY | COUNTRY STATUS | NOTES
0 | LAB | Have contacts with an international rabies reference laboratory or international collaborating/reference center been established? | 1 | FAO Reference Lab, PADOVA, Rome, Italy
0 | LAB | Has at least one human or animal rabies suspect sample been submitted to an international rabies reference laboratory for confirmation? | 1 | 2017 to FAO reference Lab
0 | CCI | Are the results of rabies sample(s) shared appropriately with local and national authorities? | 1
0 | LEG | Is a case definition available that is consistent with the OIE guidelines for animal rabies? | 1
0 | LEG | Is a case definition available that is consistent with the WHO guidelines for human rabies? | 1 | There are standard and community case definitions for human rabies
0 | LEG | Does the national authority report at least one confirmed rabies case to the WHO, OIE or PARACON? | 0
1 | DCA | Are dog rabies cases reported from a local to the national level? | 0 | There is no structure in place for reporting dog rabies cases in the animal health sector
1 | DCA | Are human rabies cases reported from a local to the national level? | 1 | There's an existing reporting structure of human rabies cases from local to national levels using the IDSR guidelines
1 | DCA | Are all human or animal rabies testing results being reported to a relevant international database such as WHO, OIE or PARACON? | 0
1 | DCA | Is there capacity to analyze dog rabies data at the national level? | 0
1 | DCA | Is there capacity to analyze human rabies data at the national level? | 1
1 | DCA | Has an animal rabies surveillance* system been established at the national level? | 0 | The process to establish a surveillance system is ongoing with full support from FAO
1 | DCA | Has a human rabies surveillance* system been established at the national level? | 1 | There is functional surveillance system established at all levels with surveillance focal persons
1 | DCA | Have reports on the number of humans bitten by dogs been compiled and reviewed? | 1 | its compliled, reviewed and placed in the weekly Epi bullettin
1 | DCA | Have dog population studies and KAP surveys been conducted to determine size, turn-over and accessibility of dogs for vaccination on a small scale? | 0
1 | PCO | Are vaccines for human rabies prophylaxis available in one or more parts of the country? | 1 | Available in all parts of the country
1 | PCO | Has the supply and access to WHO pre-qualified human rabies vaccines for PrEP for professionals at risk been ensured in local areas? | 0
1 | PCO | Are dog rabies vaccines available in at least one location in the country? | 0
1 | PCO | Has dog vaccination been initiated in some parts of the country? | 0
1 | PCO | Has Integrated Bite Case Management (IBCM)* been implemented at a local level? | 0
1 | PCO | Have Standard Operating Procedures (SOPs) for coordinated action on reported outbreaks* been established? | 0
1 | LAB | Is there capacity to conduct rabies diagnosis in at least one national laboratory (veterinary or medical laboratory)? | 1 | Central Veterinary Laboratory has the capacity to conduct rabies diagnosis, but needs strengthening
1 | LAB | Have several rabies suspect samples of animals or humans been submitted to a national laboratory and analysed? | 1 | Central Veterinary Laboratory
1 | LAB | Is animal rabies diagnosis conducted in at least one national laboratory? | 1
1 | LAB | Are rabies suspect samples of animals or humans submitted twice yearly to an international laboratory and analysed? | 0
1 | DPM | Have discussions been held with stakeholders to create a dog population management strategy at a local level? | 1 | discussions have been held among stakeholders
1 | DPM | Have you involved officials in waste management in your stakeholder meetings | 1 | Environmental Protenction Agency, City Corporations
1 | IEC | Has an assessment been done to determine what message should be communicated to the target audience at a local level? | 0
1 | IEC | Have the target audiences been identified at a local level (e.g. at-risk communities, dog owners, children)? | 0
1 | IEC | Has an IEC plan* been developed and implemented on a small scale? | 0
1 | IEC | Has broad public awareness messaging started at a national level? | 1 | During World Rabies Day 2015 & 2016
1 | IEC | Has an assessment been undertaken to determine the training needs of the professionals at a local level? | 0
1 | IEC | Have human and animal health professionals involved in rabies control been identified at a local level? | 1
1 | IEC | Has a training plan been developed at a local level? | 0
1 | IEC | Have training or refresher courses on rabies and public communication been initiated for professionals in human and animal health at a local level? | 0
1 | IEC | Has an advocacy stakeholder analysis* been done at a local level and target audiences been identified? | 0
1 | IEC | Has an advocacy plan* been developed and implemented at a local level? | 0
1 | CCI | Have the main national stakeholders in rabies prevention and control been identified? | 1
1 | CCI | Have stakeholder consultations been held within the last 3 years at the national level? | 0
1 | CCI | Has an intersectoral rabies task force, committee or working group been established at a local or national level and do they meet at least twice a year? | 1 | The Rabies TWG meets monthly
1 | CCI | Based on a small-scale experience, has a short term rabies action plan been developed and endorsed by relevant stakeholders at local / national level? | 0
1 | CCI | Have mechanisms for mobilizing emergency funds in case of an outbreak been identified? | 0
1 | LEG | Do all of the relevant professionals know the case definition for animal rabies? | 1
1 | LEG | Do all of the relevant professionals know the case definition for human rabies? | 1
1 | LEG | Is there national legislation that is relevant to rabies prevention and control? | 0
1 | LEG | If there is legislation, has it been reviewed and endorsed? | 0
1 | LEG | Has rabies been made a notifiable disease in animals? | 1
1 | LEG | Has rabies been made a notifiable disease in humans? | 1 | human rabies is one of the immediately reportable diseases in Liberia
1 | LEG | Is there legislation that includes the compulsory rabies vaccination of dogs or has it been proposed if it is not already in place? | 0
1 | LEG | Does legislation include measures for rabies outbreak response? | 0
2 | DCA | Have linked human and animal rabies surveillance systems, including agreed SOPs, been established? | 0
2 | DCA | Are human rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? | 1
2 | DCA | Are animal rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? | 0 | establishment of system in progress
2 | DCA | Is information on the epidemiology of rabies regularly shared with all stakeholders? | 1 | Information on dog bite cases are shared with stakeholders using the human health Epi Bullettin
2 | DCA | Is the on-going surveillance system for rabies being maintained? | 1 | For human health
2 | PCO | Has an assessment* been done to determine the availability and access to PEP (and PreP)? | 0
2 | PCO | Are WHO pre-qualified human rabies vaccines available and accessible in most parts of the country? | 1
2 | PCO | Are any human biologics that are not WHO-pre-qualified being phased out? (e.g. nerve tissue vaccines, low quality vaccines) | 1
2 | PCO | Are only quality dog vaccines in accordance with OIE standards being used? | 0
2 | PCO | Are dog vaccination campaigns regularly implemented in response to human cases and animal outbreaks? | 0
2 | PCO | Have IBCM SOPs, including sharing of information between sectors, been agreed upon? | 0
2 | PCO | Are SOPs available for the observation of dogs involved in biting incidents? | 0
2 | PCO | Have facilities or protocols been established for the observation of rabies-suspected dogs? | 0
2 | LAB | Is there regular laboratory diagnosis of animal rabies cases in country? | 0 | not regular
2 | LAB | Has capacity for regular sample collection and transportation been established and functioning? | 0
2 | DPM | Has a DPM* strategy and programmebeen drafted and shared with all relevant stakeholders at a local level? | 0
2 | DPM | Has the DPM strategy been finalized? | 0
2 | DPM | Has public sensitisation about DPM been built into rabies awareness campaigns at a local level? | 0
2 | DPM | Has dog population management been implemented at a local level? | 0
2 | DPM | Have training or refresher courses on animal handling and sterilisation been initiated for professionals in animal health at a local level? | 0
2 | IEC | Has an IEC plan been implemented beyond a local level? | 0
2 | IEC | Has the IEC plan been reviewed and updated? | 0
2 | IEC | Has training of human and animal health personnel been conducted in most parts of the country? | 1 | Training conducted for human health
2 | IEC | Have small-scale program successes been communicated to authorities/leaders in other parts of the country? | 0
2 | IEC | Has an advocacy stakeholder analysis* been done at a national level and have the target audiences been identified? | 0
2 | IEC | Has an advocacy campaign to national leaders/authorities been undertaken to ensure that a national rabies control strategy is created and properly resourced? | 1
2 | CCI | Are mechanisms for regular intersectoral collaboration in place and are they implemented? | 0
2 | CCI | Has the contribution and role of private sector been clarified and shared with other stakeholders? | 0
2 | CCI | Has a national strategy for rabies prevention, control and eventual elimination been drafted, shared with all relevant stakeholders and finalised? | 0
2 | CCI | Have government resources been identified and allocated in support of the national rabies control strategy? | 0
2 | LEG | Has legislation been updated to include specifications on the compulsory vaccination of dogs and the international movement of animals? | 0
3 | DCA | Have field investigations for all suspected human rabies cases been conducted? | 0 | Not for all cases
3 | DCA | Is epidemiological evidence available to rule out dog-transmitted human rabies cases? | 0
3 | DCA | Has an advocacy plan been approved by the government for local level implementation? | 0
3 | DCA | Are field investigations and laboratory confirmations conducted for all suspected rabies outbreaks in dogs? | 0
3 | DCA | Has the collection of local or national health economic and/or other disease prioritization tool data* on rabies control been initiated to make the case for rabies control investment? | 0
3 | DCA | Have the health economic data and/or other disease prioritization tool analyses been expanded to support further prioritization within the national rabies control programme? | 0
3 | PCO | Is WHO pre-qualified Pre- and Post- Exposure Prophylaxis available and accessible to high risk and exposed individuals throughout the country? | 1
3 | PCO | Are mass dog vaccination campaigns reaching at least 70% of the total dog population conducted according to the national rabies strategy? | 0
3 | PCO | Are post-vaccination surveys* in dogs being carried out to evaluate vaccination coverage? | 0
3 | PCO | Is there capacity to conduct field investigations and planned outbreak responses for animal and human rabies cases in the entire country? | 1 | limited capacities
3 | PCO | Have potential rabies-free zones been identified where canine variant cases have been absent for at least a 2 year period? | 0
3 | PCO | Has dialogue been initiated with neighbouring countries to prevent the re-introduction of rabies into designated rabies-free zones? | 0
3 | LAB | Are wildlife samples submitted for rabies laboratory diagnosis? | 0
3 | LAB | Is access to reliable laboratory diagnosis available throughout the country for animal samples (and if possible also for human and wildlife samples)? | 0
3 | LAB | Is there regular characterization and analysis of circulating rabies virus variants by a national or international laboratory? | 0
3 | DPM | Has the DPM strategy been assessed and refined based on current dog ecology or KAP surveys? | 0
3 | DPM | Have rabies awareness campaigns, including responsible dog ownership, been expanded to more areas? | 0
3 | DPM | Has veterinary and animal technician training been completed across most of country? | 0
3 | DPM | Has the dog population management strategy been implemented nationwide? | 0
3 | IEC | Has the IEC plan been integrated into the national rabies strategy and implemented at national level? | 0
3 | IEC | Have human rabies free zones been declared publicly? | 0
3 | CCI | Has the national strategy been refined based on monitoring and evaluation? | 0
3 | LEG | Is the relevant legislation enforced at the national level? | 0
4 | DCA | Are existing surveillance activities for all suspected cases in humans maintained in the country? | 0
4 | DCA | Has the epidemiological data from the routine surveillance of all animals (working animals, livestock and wildlife) been used to refine the national rabies strategy? | 0
4 | PCO | Are dog vaccination campaigns maintained in zones where dog rabies is still present or where otherwise justified (e.g. risk of introduction)? | 0
4 | PCO | Has freedom from dog-transmitted rabies in the entire country been verified by the absence of canine variant cases for at least a 2 year period? | 0
4 | PCO | Has an emergency response/contingency plan been developed to address any reintroduced case of animal rabies involving a canine variant? | 0
4 | LAB | Is there maintenance of existing surveillance activities, including ongoing laboratory investigation, for all suspected cases in dogs in the country? | 0
4 | DPM | Have dog population management and responsible dog ownership campaigns been continued after the elimination of canine-mediated human rabies? | 0
4 | IEC | Has national freedom from dog-transmitted rabies been publically declared? | 0
4 | IEC | Has national freedom from canine-mediated human rabies been publically declared? | 0
4 | CCI | Have veterinary border inspection and quarantine measures been fully implemented in accordance with national regulations? | 0
5 | PCO | Have modified protocols for PEP administration for rabies-free areas been implemented? | 0
5 | PCO | Based on risk assessments, are dog vaccination campaigns being maintained where justified? | 0
5 | PCO | Has the capacity for outbreak and re-introduction response been maintained? | 0
5 | LAB | Are there on-going laboratory investigations of all suspected cases in domestic and wild animal species in the country? | 0
5 | DPM | Have dog population management and responsible dog ownership campaigns been continued as part of the post-elimination strategy? | 0
5 | IEC | Have awareness programmes focusing on the maintenance of freedom from dog and dog transmitted human rabies been implemented? | 0
Refresh list of pending activities
Copy and paste to a new worksheet to edit

## Sheet2
STAGE | COMPONENT | ACTIVITY | NOTES
0 | LEG | Does the national authority report at least one confirmed rabies case to the WHO, OIE or PARACON?
1 | DCA | Are dog rabies cases reported from a local to the national level? | There is no system in place for reporting dog rabies cases in the animal health sector
1 | DCA | Are all human or animal rabies testing results being reported to a relevant international database such as WHO, OIE or PARACON?
1 | DCA | Is there capacity to analyze dog rabies data at the national level?
1 | DCA | Has an animal rabies surveillance* system been established at the national level? | The process to establish a surveillance system is ongoing with full support from FAO
1 | DCA | Have dog population studies and KAP surveys been conducted to determine size, turn-over and accessibility of dogs for vaccination on a small scale?
1 | PCO | Has the supply and access to WHO pre-qualified human rabies vaccines for PrEP for professionals at risk been ensured in local areas?
1 | PCO | Are dog rabies vaccines available in at least one location in the country?
1 | PCO | Has dog vaccination been initiated in some parts of the country?
1 | PCO | Has Integrated Bite Case Management (IBCM)* been implemented at a local level?
1 | PCO | Have Standard Operating Procedures (SOPs) for coordinated action on reported outbreaks* been established?
1 | LAB | Are rabies suspect samples of animals or humans submitted twice yearly to an international laboratory and analysed?
1 | IEC | Has an assessment been done to determine what message should be communicated to the target audience at a local level?
1 | IEC | Have the target audiences been identified at a local level (e.g. at-risk communities, dog owners, children)?
1 | IEC | Has an IEC plan* been developed and implemented on a small scale?
1 | IEC | Has an assessment been undertaken to determine the training needs of the professionals at a local level?
1 | IEC | Has a training plan been developed at a local level?
1 | IEC | Have training or refresher courses on rabies and public communication been initiated for professionals in human and animal health at a local level?
1 | IEC | Has an advocacy stakeholder analysis* been done at a local level and target audiences been identified?
1 | IEC | Has an advocacy plan* been developed and implemented at a local level?
1 | CCI | Have stakeholder consultations been held within the last 3 years at the national level?
1 | CCI | Based on a small-scale experience, has a short term rabies action plan been developed and endorsed by relevant stakeholders at local / national level?
1 | CCI | Have mechanisms for mobilizing emergency funds in case of an outbreak been identified?
1 | LEG | Is there national legislation that is relevant to rabies prevention and control?
1 | LEG | If there is legislation, has it been reviewed and endorsed?
1 | LEG | Is there legislation that includes the compulsory rabies vaccination of dogs or has it been proposed if it is not already in place?
1 | LEG | Does legislation include measures for rabies outbreak response?
2 | DCA | Have linked human and animal rabies surveillance systems, including agreed SOPs, been established?
2 | DCA | Are human rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)?
2 | DCA | Are animal rabies surveillance systems, including feedback mechanisms, functioning and coordinated between administrative levels (national, province, district, municipal, etc.)? | establishment of system in progress
2 | PCO | Has an assessment* been done to determine the availability and access to PEP (and PreP)?
2 | PCO | Are only quality dog vaccines in accordance with OIE standards being used?
2 | PCO | Are dog vaccination campaigns regularly implemented in response to human cases and animal outbreaks?
2 | PCO | Have IBCM SOPs, including sharing of information between sectors, been agreed upon?
2 | PCO | Are SOPs available for the observation of dogs involved in biting incidents?
2 | PCO | Have facilities or protocols been established for the observation of rabies-suspected dogs?
2 | LAB | Is there regular laboratory diagnosis of animal rabies cases in country? | not regular
2 | LAB | Has capacity for regular sample collection and transportation been established and functioning?
2 | DPM | Has a DPM* strategy and programmebeen drafted and shared with all relevant stakeholders at a local level?
2 | DPM | Has the DPM strategy been finalized?
2 | DPM | Has public sensitisation about DPM been built into rabies awareness campaigns at a local level?
2 | DPM | Has dog population management been implemented at a local level?
2 | DPM | Have training or refresher courses on animal handling and sterilisation been initiated for professionals in animal health at a local level?
2 | IEC | Has an IEC plan been implemented beyond a local level?
2 | IEC | Has the IEC plan been reviewed and updated?
2 | IEC | Have small-scale program successes been communicated to authorities/leaders in other parts of the country?
2 | IEC | Has an advocacy stakeholder analysis* been done at a national level and have the target audiences been identified?
2 | CCI | Are mechanisms for regular intersectoral collaboration in place and are they implemented?
2 | CCI | Has the contribution and role of private sector been clarified and shared with other stakeholders?
2 | CCI | Has a national strategy for rabies prevention, control and eventual elimination been drafted, shared with all relevant stakeholders and finalised?
2 | CCI | Have government resources been identified and allocated in support of the national rabies control strategy?
2 | LEG | Has legislation been updated to include specifications on the compulsory vaccination of dogs and the international movement of animals?
3 | DCA | Have field investigations for all suspected human rabies cases been conducted? | Not for all cases
3 | DCA | Is epidemiological evidence available to rule out dog-transmitted human rabies cases?
3 | DCA | Has an advocacy plan been approved by the government for local level implementation?
3 | DCA | Are field investigations and laboratory confirmations conducted for all suspected rabies outbreaks in dogs?
3 | DCA | Has the collection of local or national health economic and/or other disease prioritization tool data* on rabies control been initiated to make the case for rabies control investment?
3 | DCA | Have the health economic data and/or other disease prioritization tool analyses been expanded to support further prioritization within the national rabies control programme?
3 | PCO | Are mass dog vaccination campaigns reaching at least 70% of the total dog population conducted according to the national rabies strategy?
3 | PCO | Are post-vaccination surveys* in dogs being carried out to evaluate vaccination coverage?
3 | PCO | Have potential rabies-free zones been identified where canine variant cases have been absent for at least a 2 year period?
3 | PCO | Has dialogue been initiated with neighbouring countries to prevent the re-introduction of rabies into designated rabies-free zones?
3 | LAB | Are wildlife samples submitted for rabies laboratory diagnosis?
3 | LAB | Is access to reliable laboratory diagnosis available throughout the country for animal samples (and if possible also for human and wildlife samples)?
3 | LAB | Is there regular characterization and analysis of circulating rabies virus variants by a national or international laboratory?
3 | DPM | Has the DPM strategy been assessed and refined based on current dog ecology or KAP surveys?
3 | DPM | Have rabies awareness campaigns, including responsible dog ownership, been expanded to more areas?
3 | DPM | Has veterinary and animal technician training been completed across most of country?
3 | DPM | Has the dog population management strategy been implemented nationwide?
3 | IEC | Has the IEC plan been integrated into the national rabies strategy and implemented at national level?
3 | IEC | Have human rabies free zones been declared publicly?
3 | CCI | Has the national strategy been refined based on monitoring and evaluation?
3 | LEG | Is the relevant legislation enforced at the national level?
4 | DCA | Are existing surveillance activities for all suspected cases in humans maintained in the country?
4 | DCA | Has the epidemiological data from the routine surveillance of all animals (working animals, livestock and wildlife) been used to refine the national rabies strategy?
4 | PCO | Are dog vaccination campaigns maintained in zones where dog rabies is still present or where otherwise justified (e.g. risk of introduction)?
4 | PCO | Has freedom from dog-transmitted rabies in the entire country been verified by the absence of canine variant cases for at least a 2 year period?
4 | PCO | Has an emergency response/contingency plan been developed to address any reintroduced case of animal rabies involving a canine variant?
4 | LAB | Is there maintenance of existing surveillance activities, including ongoing laboratory investigation, for all suspected cases in dogs in the country?
4 | DPM | Have dog population management and responsible dog ownership campaigns been continued after the elimination of canine-mediated human rabies?
4 | IEC | Has national freedom from dog-transmitted rabies been publically declared?
4 | IEC | Has national freedom from canine-mediated human rabies been publically declared?
4 | CCI | Have veterinary border inspection and quarantine measures been fully implemented in accordance with national regulations?
5 | PCO | Have modified protocols for PEP administration for rabies-free areas been implemented?
5 | PCO | Based on risk assessments, are dog vaccination campaigns being maintained where justified?
5 | PCO | Has the capacity for outbreak and re-introduction response been maintained?
5 | LAB | Are there on-going laboratory investigations of all suspected cases in domestic and wild animal species in the country?
5 | DPM | Have dog population management and responsible dog ownership campaigns been continued as part of the post-elimination strategy?
5 | IEC | Have awareness programmes focusing on the maintenance of freedom from dog and dog transmitted human rabies been implemented?

## RULES (hidden)
RULES FOR STAGE PROGRESSION
SCORE | RULE
+ 1 | All critical activities (see hidden Key Activities worksheet) accomplished
+ 0.5 | 50% or more of the critical activities checked
+ 0.5 | Not all but at least 1 critical activity checked, AND 50% +1 of all activities checked
+ 0 | At least 1 critical activity checked, AND 50% or less of all activities checked
+ 0 | No critical activity accomplished